## Sheet1
Load datasets
Sam | Read craiglist scraped file into a pandas dataframe
Sam | Read truecar.com scraped file into a pandas dataframe
Sam | Record record counts for report file
Sam | Take a subset of each to use for development/testing
Sam | Merge into a consolidated testing dataframe |  |  | 100 total, 50 from each (potentially one make/manufacturer)
Sam | Merge into a consolidated complete dataframe |  |  | 500 total, 250 from each (potentially one make/manufacturer)
Data cleaning
Steven / All | Drop unneeded columns
Steven / All | Find number of occurrences of duplicate VINs and remove duplicate
Steven / All | Add columns for:
Steven / All |  | Sales channel: Auction vs Public
Steven / All |  | Problem: True or False (if there is some problem with this row of data, for later investigation)
Steven / All | Assign sales by Auction vs Public based on vehicle age (preliminary, this may change based on results of the safety rating API)
Steven / All |  | Create Vehicle Age column
Steven / All |  | Calculate vehicle age for every vehicle in the dataset
Steven / All |  | For every record that is 20 years old or older, flag as Auction Sales Channel
Steven / All |  | For every record that is < 20 years old , flag as Public Sales Channel
Steven / All | Assign sales by Auction vs Public based on vehicle condition
Steven / All |  | If there is condition data available for each car:
Steven / All |  |  | Assign sales by Auction for cars if the condition is poor, not running, etc…
Steven / All | Flag problem records
Steven / All |  | If a record has a NaN in a critical column, use True in the Problem column
US State to Main Office Lookup
Roopa | Create "About US" page based on the Main Office List .csv file
Roopa | Use pandas read_html to scrape About US page and store into a dataframe
Roopa | Go through car inventory dataframe and assign each car a Main Office (new column to dataframe)
API -Overall Safety Rating
Roopa | Create a column in the cars dataframe
Roopa | For each car in the dataframe
Roopa |  | Call the API and retrieve the overall safety rating
Roopa |  | Assign the rating in the dataframe row for the car
Write Car inventory to Mongo DB
Roopa | Create a TrueSafeCars central DB
Roopa | Create a main cars inventory collection
Roopa |  | Determine columns to store the following data
API - Open Recall Data
Steven / All | Once the car inventory is in mongoDB
Steven / All |  | For every car record in our collection
Steven / All |  |  | Call the API for open recall data
Steven / All |  |  | If open recall data exists, push to an array of recall data for that car